# Project Mandate - Coralvale Regional Council - 25/09/2026

# Mandate Header (From, To, Background)

| Field | Entry |
| --- | --- |
| Council | Coralvale Regional Council (QLD) |
| Subject | Ridgeback Creek Water Treatment Plant |
| Date | 25/09/2026 |
| From | J. Smith, Manager Capital Delivery |
| To | Director Infrastructure Services |
| Prepared for | Chief Executive Officer and Executive Leadership Team |
| Background | Council resolved Option 3 in June 2026. Practical Completion is locked to the State grant funding deed. Wet season constrains the construction window. |

# Strategic Problem or Opportunity Statement

Ridgeback Creek Water Treatment Plant is at IPWEA NAMS+ Condition Grade 4 with a single 1980s clarifier train, manual dosing and no redundancy. Peak-day demand now exceeds firm capacity.

The problem statement is a present shortfall, not a forecast one. On peak days the plant cannot meet demand from its firm capacity. With a single clarifier train and no redundancy, there is no standby if that train is out of service.

Council has already resolved Option 3 as the response. The decision now sought is whether to authorise the work needed to deliver it within the funding and timing conditions set out below.

# Project Objectives & Corporate Alignment

The target state is: A fully automated plant with 25 MLD firm capacity, duty/standby trains, SCADA integration and 1-in-100 year flood immunity.

The project objectives are to:

- Close the firm capacity shortfall by delivering 25 MLD firm capacity. Whether 25 MLD meets current and forecast peak-day demand is [VERIFY], and the Project Brief must confirm it.

- Remove the single point of failure by providing duty/standby trains.

- Replace manual dosing with full automation and SCADA integration.

- Provide 1-in-100 year flood immunity.

- Reach Practical Completion by 15/12/2027, as required by the State grant funding deed.

Corporate Plan alignment: the project maps to the Coralvale Corporate Plan 2024-2029, Pillar 3 Sustainable Infrastructure, Goal 3.2. Its borrowing component is funded through the Long Term Financial Plan 2024-2034. The project therefore sits within Council's existing strategic and financial plans, and authorising it does not require a new strategic direction.

# Scope Envelope & Constraints

The scope envelope is delivery of Option 3 at Ridgeback Creek Water Treatment Plant to the target state above, within the budget ceiling, procured by open public tender. At $18,500,000 ex-GST, the capital value is above the $200,000 ex-GST procurement threshold in the Coralvale Regional Council Procurement Policy 2026, adopted 24/06/2026, which is consistent with the resolved open public tender.

| Milestone | Date | Driver |
| --- | --- | --- |
| Tender advertised | 01/2027 |  |
| Tender award | 03/2027 | Set to clear the wet season |
| Construction start | 05/2027 |  |
| Practical Completion | 15/12/2027 | State grant funding deed |
| Defects liability ends | 15/12/2028 |  |

The key constraints are:

- Practical Completion on 15/12/2027 is a funding condition under the State grant funding deed, not a scheduling preference.

- Tender award in 03/2027 is set to clear the wet season. A late award pushes construction toward the wet season, which constrains the construction window.

- As Step 1 of the PRINCE2 chain, this Project Mandate must be followed by the Project Brief and Business Case before tender advertisement in 01/2027.

Further constraints, scope exclusions and key stakeholders are [VERIFY].

# Initial Budget Ceiling & Funding Envelope

The budget ceiling is $18,500,000 ex-GST in capital expenditure, capped by Council decision.

| Funding source | Amount (ex-GST) |
| --- | --- |
| Borrowings under the Long Term Financial Plan 2024-2034 | $13,500,000 |
| Works for Queensland grant | $5,000,000 |
| Total budget ceiling | $18,500,000 |

Operating expenditure reduces by $1,200,000 per year; the GST basis of this figure is [VERIFY].

Because the ceiling is capped, any cost growth found during start-up must be managed inside this envelope. Whether the Works for Queensland grant is the funding under the State grant funding deed is [VERIFY]; if it is, the $5,000,000 ex-GST grant depends on meeting Practical Completion.

# Nominated Project Sponsor & Manager

The nominated Project Sponsor is the Director Infrastructure Services. The Sponsor's financial delegation limit under the Council Delegations of Authority Register (CEO/Director Financial Limits) is [VERIFY] and must be confirmed against the $18,500,000 ex-GST budget ceiling before sign-off. A Project Manager has not yet been appointed; the nominated Project Manager is [VERIFY].

# Authority to Proceed (Sign-off)

Signing this Project Mandate gives authority to proceed with the PRINCE2 Starting Up a Project (SU) Process and triggers initial exploratory resource spend. It does not approve the Project Brief, Business Case or tender. The decision-maker for this authority is [VERIFY]. This matter is for consideration in open session.

| Field | Entry |
| --- | --- |
| Authorised by (signature) |  |
| Name and position |  |
| Date (DD/MM/YYYY) |  |